## Estimation_Technology_Date
LLW Incorporated
Screen / Feature Name(s) | Feature Name | Priority | Best Case | Most Likely | Worst Case | Projections / Actuals | P/A | Notes | P1 B | P1 M | P1 W | P2 B | P2 M | P2 W | P2 A
Documentation | Technical Design Document | 1 | 10 | 16 | 24 |  |  | Create, Review, Release TDD, Maintain | 10 | 16 | 24 | 0 | 0 | 0
Project Setup | Setup | 1 | 4 | 6 | 8 |  |  | Create new git repo, establish .gitignore, establish blank project, commit, branch, team clone. | 4 | 6 | 8 | 0 | 0 | 0
Data Model - Shopping List | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 | 0 | 0 | 0
Data Model - Shopping List Item | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 | 0 | 0 | 0
Data Model - Note | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 | 0 | 0 | 0
Add new items | Adding Items | 2 | 6 | 8 | 16 |  |  | The ability to add new items into the shopping list | 0 | 0 | 0 | 6 | 8 | 16
Persist items to database | Items to database | 2 | 6 | 8 | 10 |  |  | All Items are collected in the database. | 0 | 0 | 0 | 6 | 8 | 10
Check off items | Check off items | 2 | 8 | 14 | 16 |  |  | Make Check boxes for each line item. | 0 | 0 | 0 | 8 | 14 | 16
Clear items | Clear items | 2 | 2 | 4 | 6 |  |  | The ability to delete items and lists on screen and Database. | 0 | 0 | 0 | 2 | 4 | 6
Ordering of items | Ordering of items | 3 | 4 | 6 | 8 |  |  | To change the order of the items. | 0 | 0 | 0 | 0 | 0 | 0
Sorting of items | Sorting of items | 3 | 4 | 6 | 8 |  |  | To sort items in a list. | 0 | 0 | 0 | 0 | 0 | 0
Delete Indivdual items | Delete items | 3 | 2 | 4 | 6 |  |  | To be able to delete items in the database | 0 | 0 | 0 | 0 | 0 | 0
Edit Items | Edit items | 3 | 1 | 2 | 3 |  |  | ability to edit the items in the list. | 0 | 0 | 0 | 0 | 0 | 0
Add notes to items | Add notes | 3 | 1 | 2 | 3 |  |  | make a note on each item. | 0 | 0 | 0 | 0 | 0 | 0
Multiple User | Multiple users | 4 | 4 | 6 | 8 |  |  | logins for multiple users. | 0 | 0 | 0 | 0 | 0 | 0
Login and Auth | Login | 4 | 1 | 2 | 3 |  |  | Authorizing each login. | 0 | 0 | 0 | 0 | 0 | 0
Grouping of lists | Grouping of lists | 4 | 2 | 4 | 6 |  |  | The ability to make all list show up on one screen. | 0 | 0 | 0 | 0 | 0 | 0
List Template | List Template | 4 | 4 | 6 | 8 |  |  | Ability to print the list. | 0 | 0 | 0 | 0 | 0 | 0
Web API | API | 4 | 6 | 8 | 10 |  |  | download software on mobile device. | 0 | 0 | 0 | 0 | 0 | 0
Developer portal | Dev portal | 4 | 6 | 8 | 10 |  |  | To have a deployed in developer mode. | 0 | 0 | 0 | 0 | 0 | 0
Deployment | Deploy |  | 1 | 2 | 3 |  |  | Setting the program up to be accessed on servers at a hosting site like Azure. | 0 | 0 | 0 | 0 | 0 | 0
Apply Design Template | Design |  | 12 | 16 | 20 |  |  | The front-end work on the site to make it attractive. | 0 | 0 | 0 | 0 | 0 | 0
Testing | Test |  | 6 | 8 | 10 |  |  | Author test plan, test cases, log bugs | 0 | 0 | 0 | 0 | 0 | 0
|  | Priority | Best Case | Most Likely | Worst Case | Projected / Actuals
TOTAL HOURS - DEVELOPMENT ONLY |  | All | 92 | 138 | 186 | 0 | P/A
Priority 1 Only |  | 1 | 16 | 24 | 32 | #REF! | P/A |  | 16 | 24 | 32 | 22 | 34 | 48 | 0
Priority 2 Only |  | 2 | 22 | 34 | 48 | 0 | P/A
TOTAL HOURS WITH RESOURCES - ALL | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 31.28 | 46.92 | 63.24
Apprentice 2 | 100% | 33% | 30.36 | 45.54 | 61.38
Apprentice 3 | 100% | 33% | 30.36 | 45.54 | 61.38
100%
PM |  | 20% | 18.4 | 27.6 | 37.2
Test |  | 20% | 18.4 | 27.6 | 37.2
TOTAL HOURS WITH RESOURCES- P1 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 5.44 | 8.16 | 10.88
Apprentice 2 | 100% | 33% | 5.28 | 7.92 | 10.56
Apprentice 3 | 100% | 33% | 5.28 | 7.92 | 10.56
100%
PM |  | 20% | 3.2 | 4.8 | 6.4
Test |  | 20% | 3.2 | 4.8 | 6.4
TOTAL HOURS WITH RESOURCES - P2 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 7.48 | 11.56 | 16.32
Apprentice 2 | 100% | 33% | 7.26 | 11.22 | 15.84
Apprentice 3 | 100% | 33% | 7.26 | 11.22 | 15.84
100%
PM |  | 20% | 4.4 | 6.8 | 9.6
Test |  | 20% | 4.4 | 6.8 | 9.6

## Libraries
Library Name | Priority | Notes

## Images
Images Needed
Screen | Image | Notes

## Version History
Version | Date | Author | Notes
1 |  |  | Initial Draft
2
3
4
5
6

## References
Reference Name | Location | Filename / Notes